## Phase3-TeamPlanning2022-csv
CSI4142 - Project 2022
Phase 4 - Data Mining
Teamwork - breakdown of duties
Deliverable checklist | Responsible | Expected completion date | Actual completion date | Estimated | Actual | Notes (if any)
| team member(s) |  |  | time (hours) to complete | time (hours) to complete
Data preprocessing
Data summarisation | Langqing Zou | 3.25 | 3.27 | 1 hour | 1 hour
.. Visualisation of attributes | Langqing Zou | 3.25 | 3.27 | 1 hour | 1 hour
Data transformation | Langqing Zou | 3.25 | 3.27 | 1 hour | 1 hour
.. Missing values | Langqing Zou | 3.25 | 3.27 | 1 hour | 1 hour
.. Categorical data | Langqing Zou | 3.25 | 3.27 | 1 hour | 1 hour
.. Numeric data | Langqing Zou | 3.25 | 3.27 | 1 hour | 1 hour
.. Feature selection | Langqing Zou
Data mining - Classification
Decision tree | Kangwei Liao | 4.1 | 4.3 | 30 mins | 35 mins
Gradient Boosting | Kangwei Liao | 4.1 | 4.3 | 31 mins | 36 mins
Random Forests | Kangwei Liao | 4.1 | 4.3 | 32 mins | 37 mins
Comparison of results | Kangwei Liao | 4.1 | 4.3 | 33 mins | 38 mins
Summary | Kangwei Liao | 4.1 | 4.3 | 34 mins | 39 mins
Anomaly detection
One-class SVM | Kangwei Liao, Langqing Zou | 4.2 | 4.5 | 30 minr | 2 hours
Summary | Kangwei Liao, Langqing Zou | 4.2 | 4.5 | 30 min | 2 hours
Other tasks - please specify